## Issues Log
Issues Log
Issues #	Issue	Date Identified	Due Date	Identified By	Assigned To	Status	Process Categories	Solution	Date Completed
1	Valley and Quan not available until July 15, 2019	05/02/19	06/01/19	Neil Callahan	Tony DiBello	Red	Closed	Find additional IT team members	05/10/19
2	Associates may be unwilling to learn new tools	04/23/19	06/01/19	Jeff Brown	Richard Contin	Yellow	Closed	Demonstrate simplicity and benefits	05/15/19
3	Subject matter experts are busy during interview time period	07/21/19	09/21/19	Monica Ianucci	Tony DiBello	Green	In Process	Adminster questionnaires before interviews	NA

					Open
					Team Member Name	Red, Yellow, Green	Closed
					Deffered
					In Process
					Re-opened