## Lessons Learned
Date	ID #	Experience or Issue Logged	Impact on Project	Description of Leasons Learned	Best Practice to Follow for Future Projects
05/10/19	1	Team members unavailable when needed	High	Team should be built around member availability	Determine and report availability prior to finalizing the team
07/21/19	2	Subject matter experts are overwhelmed during interview period	Medium	Interview period should be flexible or extended, or other methods used	Administer questionnaires on top of interviews
09/11/19	3	Language and communication barriers make it harder to consume content	Medium	Global teams of sales associates cannot use a single form of content	Create content in multiple languages and forms
11/17/19	4	Certain activities take up too much time for team members	Low	Consider and/or leave open the possibility of outsourcing activities	Determine priority and time consumption of activities in planning
12/21/19	5	Stakeholders don’t have ways of getting updates when they want them	Low	Push communication is not always the best for many stakeholders	Utilize pull and interactive communication where possible