## Sheet1
Project Schedule with Milestones Project Planning Part E
	2019
Project Milestones (Hightower Global Solutions)	June	July	Aug	Sep	Oct	Nov	Dec
User Interface Design Complete and Tested
Style Sheets for Portal
Theme Design for Website
Portal Administration Complete and Accepted
Administrative Page Groups
Administrative Access Control Design
Content Management & Coding Complete and Tested
Content Display from Repository
Content Upload and Functionality
Configure/Code Indexing and Functionality
Architecture Approved for Implementation
Servers for Development, Staging, and Production
Configure Firewalls
Integrate Infrastructure and Security Systems
Log-in/Registration System Complete and Tested
Create Log-in/User Profiles
Product Content Modules Completed and Accepted
Interviews with Subject Matter Experts (SMEs) and Sales Representatives
Product Sales Summaries
Sales Case Studies for Content Modules
Edit/Film SME Videos
Upload Presentations, Demos, and Webinars for Content Modules
Development and Document Coding Standards and Procedures
Develop Test Acceptance Plans and Procedures
HighLEARN Database Test and Acceptance