## Sheet1
Project Schedule with Tasks -- Duration/Resources-- Project Planning Part F
			2019
Project Tasks (Hightower Global Solutions)	Duration in Days	Resource Assigned	June	July	Aug	Sep	Oct	Nov	Dec
User Interface Design Complete and Tested	2	Felipe
Style Sheets for Portal	21	Ianucci
Theme Design for Website	56	Contin
Portal Administration Complete and Accepted	2	DiBello
Administrative Page Groups	70	Felipe
Administrative Access Control Design	49	Xiao
Content Management & Coding Complete and Tested	2	Ianucci
Content Display from Repository	28	Brant
Content Upload and Functionality	56	Contin
Configure/Code Indexing and Functionality	91	Quan
Architecture Approved for Implementation	1	Quan
Servers for Development, Staging, and Production	91	Valley
Configure Firewalls	28	Valley
Integrate Infrastructure and Security Systems	56	Valley
Log-in/Registration System Complete and Tested	3	Quan
Create Log-in/User Profiles	28	Quan
Product Content Modules Completed and Accepted	5	Contin
Interviews with Subject Matter Experts (SMEs) and Sales Representatives	14	Ianucci
Product Sales Summaries	28	Contin
Sales Case Studies for Content Modules	49	Brant
Edit/Film SME Videos	7	Ianucci
Upload Presentations, Demos, and Webinars for Content Modules	14	Brant
Development and Document Coding Standards and Procedures	105	Quan
Develop Test Acceptance Plans and Procedures	105	Contin
HighLEARN Database Test and Acceptance	7	Quan