## Sheet1
Project Schedule with Tasks -- Duration/Resources-- Project Planning Part G
					2019
Project Tasks (Hightower Global Solutions)	Duration in Days	Resource Assigned	Labor Rate per Day	Estimated New Cost	June	July	Aug	Sep	Oct	Nov	Dec
User Interface Design Complete and Tested	2	Felipe	30000	$60,000
Style Sheets for Portal	21	Ianucci	1500	$31,500
Theme Design for Website	56	Contin	3200	$179,200
Portal Administration Complete and Accepted	2	DiBello	1700	$3,400
Administrative Page Groups	70	Felipe	350	$24,500
Administrative Access Control Design	49	Xiao	1900	$93,100
Content Management & Coding Complete and Tested	2	Ianucci	22500	$45,000
Content Display from Repository	28	Brant	3300	$92,400
Content Upload and Functionality	56	Contin	40	$2,240
Configure/Code Indexing and Functionality	91	Quan	5800	$527,800
Architecture Approved for Implementation	1	Quan	160	$160
Servers for Development, Staging, and Production	91	Valley	130	$11,830
Configure Firewalls	28	Valley	4500	$126,000
Integrate Infrastructure and Security Systems	56	Valley	3000	$168,000
Log-in/Registration System Complete and Tested	3	Quan	2100	$6,300
Create Log-in/User Profiles	28	Quan	150	$4,200
Product Content Modules Completed and Accepted	5	Contin	500	$2,500
Interviews with Subject Matter Experts (SMEs) and Sales Representatives	14	Ianucci	2300	$32,200
Product Sales Summaries	28	Contin	1450	$40,600
Sales Case Studies for Content Modules	49	Brant	75	$3,675
Edit/Film SME Videos	7	Ianucci	2800	$19,600
Upload Presentations, Demos, and Webinars for Content Modules	14	Brant	150	$2,100
Development and Document Coding Standards and Procedures	105	Quan	12	$1,260
Develop Test Acceptance Plans and Procedures	105	Contin	18	$1,890
HighLEARN Database Test and Acceptance	7	Quan	1050	$7,350