## Stakeholder Concerns
Project Concern #	Description of Concern Identified	Impact on Project	Date Identified	Due Date for Completion	Stakeholder that Identified Concern	Internal or External Stakeholder	Project Team Member Concern Assigned To:	Solution	Date Completed
1	Sales associates may be reluctant to familiarize themselves with the new tool	Medium	04/23/19	06/01/19	Neil Callahan	Internal	Richard Contin	Demonstrate the vision of the intranet and its simplicity. Explain the benefits that it will have for associates who buy in to learning and growing their product knowledge	05/15/19
2	Steve Quan and Shannon Valley are unavailable until mid-July, and IT personnel are needed to kick off the portal development at the beginning of the project	High	05/02/19	06/01/19	Jeff Brown	Internal	Tony DiBello	Secure additional project team members from the systems engineering department	05/10/19
3	Marketing department believes it would be easier to utilize Microsoft’s Sharepoint software that hosts the company-wide intranet	Low	05/25/19	07/31/19	Chris Gentile	Internal	Tony DiBello	Once the portal has been designed and sample content is available, take time to meet with marketing leaders and show the benefit of owning this software	TBD
4	As the company continues its aggressive acquisition strategy, the portal may quickly become outdated	Medium	05/30/19	12/31/19	Nicole Smith	Internal	Monica Ianucci	Monica volunteered to own the portal’s content at the close of the project. She has a good relationship with Product Director, Melvin Simpson, who is familiar with the company’s product offerings at all times	TBD