## Stakeholder Concerns
Project Task Number	Description of Task	Planned Duration in Days	Planned Start Date	Planned Completion Date	Estimated Labor, Material, Etc. required to complete the project	Number of Units Required	Estimated Cost per Unit	Estimated Cost in Dollars
1	Document existing lighting fixtures and types, including housings, dimensions, and method of installation that must be addressed as part of retrofit recommendations	6	09/01/21	09/07/21	Matt Stevens, Strategic Planning Assistant	12	40	$480.00
2	Measure all existing lighting levels of each space and functions/personnel that operate there	3	09/07/21	09/10/21	Matt Stevens, Strategic Planning Assistant	5	100	$500.00
3	Determine final quantity, type, and location of existing fixtures, lamps, and ballasts to be replaced	2	09/10/21	09/12/21	Matt Stevens, Strategic Planning Assistant	2	40	$80.00
4	Identify areas that will have occupancy controls or motion detectors to turn off lights when space is unoccupied	5	09/12/21	09/17/21	Matt Stevens, Strategic Planning Assistant	1	160	$160.00
5	Provide total number of recommended lighting components and related costs	1	09/17/21	09/18/21	Matt Stevens, Strategic Planning Assistant	4	100	$400.00
6	Life cycle cost analysis and economic evaluation that factors in cost, maintenance cost, and utility cost over the expected life of the building lighting retrofit	4	09/18/21	09/22/21	Perry Silverman, Finance Analyst	7	1000	$7,000.00
7	Waste management plan for disposal of hazardous materials, submitted in accordance with EPA guidelines	2	09/22/21	09/24/21	Trudy Noble, Environmental Manager	10	450	$4,500.00
8	Procurement of necessary retrofit materials and electrical components	5	09/24/21	09/29/21	Paul Callahan, Distribution Logistics Manager	30	200	$6,000.00
9	Detailed demolition and installation requirements, including procedures to shut down electric, disarm fire alarm system, remove materials from property, and protect computer and other equipment	3	09/29/21	10/02/21	Emmitt McAuley, OSHA liaison	5	200	$1,000.00
10	Completion of all necessary permit applications and certificates	4	10/02/21	10/06/21	Jeff Salvatore, PR/Communications Manager	18	160	$2,880.00
11	Plan to comply with all Occupational Safety and Health Program requirements (containment of dust, debris, contaminants)	1	10/06/21	10/07/21	Trudy Noble, Environmental Manager	4	275	$1,100.00
12	Submission of drawings and construction phase schedule	2	10/07/21	10/09/21	Vivian Liu, Project Manager	100	25	$2,500.00
13	Completion of Phase 1 lighting replacement: Corporate offices	6	10/09/21	10/15/21	Vivian Liu, Project Manager	50	80	$4,000.00
14	Completion of Phase 2 lighting replacement: Production shop offices and break rooms	4	10/15/21	10/19/21	Vivian Liu, Project Manager	44	80	$3,520.00
15	Completion of Phase 3 lighting replacement: Production floor	10	10/19/21	10/29/21	Vivian Liu, Project Manager	250	80	$20,000.00
16	Completion of Phase 4 lighting replacement: Warehouse and parking lots	8	10/29/21	11/06/21	Vivian Liu, Project Manager	80	80	$6,400.00
17	Installation of sensors and motion detectors	10	11/06/21	11/16/21	Elwood Vaughn, Systems/IT Director	35	120	$4,200.00
18	Delivery of computer model with baseline energy usage and automated tracking system	7	11/16/21	11/23/21	Elwood Vaughn, Systems/IT Director	110	65	$7,150.00
19	Submission of project close-out documentation	5	11/23/21	11/28/21	Matt Stevens, Strategic Planning Assistant	3	300	$900.00
Total Cost for Project								$72,770.00