## Sheet1
Project Schedule with Tasks -- Duration/Resources-- Project Planning Part G
					2012		2013					2014
Project Tasks (ECO-Trans)	Duration in Days	Resource Assigned	Labor Rate per Day	Estimated New Cost	Nov	Dec	Jan	Feb	Mar	Apr	May	June	July	Aug	Sep	Oct	Nov	Dec	Jan	Feb
Project initiation	100	Varga	100	$10,000
System test	25	Operations	350	$8,750
Confirm funding	10	Finance	50	$500
Central control room	75	Engineers	425	$31,875
Swap defective for new components	15	Varga	20	$300
Equip first phase of locomotives	90	Engineers	800	$72,000
Manually inspect new components	3	Varga	60	$180
Reassemble terminal casings	7	Assembly Team	200	$1,400
Reassign training specialists	10	Vonn/Beauchamp	300	$3,000
Resolve resource calendar conflicts	1	Varga	50	$50
Manage SRT team member conflict	5	Varga	75	$375
Send product specialist for demo	2	Hermann	250	$500
Equip entire fleet	30	Engineers	1000	$30,000
Complete end user training	6	Varga	100	$600