Module 8: Project Monitoring and Control
9/13

Learning Objectives
1. Assess closure activities needed to effectively close out a project
2. Analyze the role of the project manager throughout the implementation of the project

Monitoring and Controlling Project Work
- Monitoring and Controlling Project Work
  - tracking, reviewing, and regulating project progress to ensure that it meets the objectives defined in the project plan
    - adjustments to project activities will have to be made to keep the project on course to meet its objectives
    - practitioners will need to act quickly to ensure that the change is handled appropriately before it can disrupt project activities
  - essential to ensuring an efficient and effective workflow throughout a project
  - concerned with
    - comparing actual project performance against what was planned for in the project plan
    - assessing performance to determine whether action needs to be taken to keep the project on course
    - monitoring changes as they are implemented
    - tracking and analyzing existing risks (and identifying new risks) to ensure that risks do not threaten the project or its deliverables
    - updating project plans and baselines
    - communicating performance reports to appropriate project participants
    - developing and maintaining an information base of project successes and challenges
  - monitoring
    - involves the collection, recording, and reporting of information about the project
  - controlling
    - using this info to ensure that the project is achieving what it is designed to achieve
- Aligning Work with Project Plans
  - project plan acts as the basis for monitoring project activities and knowing when to take corrective action
  - assess project progress by comparing the work produced, effort, cost, and schedule to the baselines that were created.
  - use milestones, the project schedule, and the work breakdown structure (WBS) to check performance and to select times for monitoring and controlling efforts.
  - review the responsibility assignment matrix to ensure that responsible parties are aware of and are completing their work assignments.
  - monitor and review contractor performance to ensure that the work produced complies with the agreements signed.
  - review and update the project's risk register to ensure that existing risks are monitored and new risks that could affect the project are detected and planned for
- Monitoring Risk
  - review and update risk register items in regular meetings
- Ensuring Project Alignment
  - key benefit of monitoring and controlling
  - project performance will be measured regularly to ensure that it aligns with the objectives of the project plan
  - actions needed to realign work activities can be quickly implemented and problems can be resolved before they disrupt the project

Risk Monitoring and Controlling
- Reviewing the Risk Register
  - review the items on the risk register frequently and to revise as needed
  - certain risks may no longer be possible or their potential impact may have decreased to a negligible level
  - may also discover new risks
    - those that they hadn't thought of before
    - secondary risks that occurred as they implemented risk responses
      - as a result of the response implemented previously
    - appropriate responses will have to be developed and assigned to appropriate parties
- Strategies for Addressing Risks
  - Negative Risk Responses
    - Avoid the risk
    - Mitigate the threat
    - Transfer the risk to another group or organization
    - Accept the risk
  - Positive Risk Responses
    - Exploit the risk
    - Share the risk with another organization
    - Enhance the opportunity
    - Accept the risk

The Change Control Process
- not all change requests are good for the project
  - may not bring enough value to the project to merit inclusion
  - may create significant disruption to existing work
- it is the responsibility of the project leader or project manager to (either individually or as part of a change control team)
  - evaluate calls for change
  - implement those that will add benefit to the project work
- Evaluating the Request
  - first task is to review the change request forms and evaluate their merit
    - important to be evaluated objectively and impartially
      - helps to foster an environment of trust and inclusion
  - the impact on all of the project parameters must be evaluated
    - a change to one part of the project will likely require adjustments in others
  - if it’s necessary, determine if the change is possible, given the existing plan
    - Is there enough time in the schedule to enact the change?
    - Are resources available to implement it?
    - Is there enough money in the budget to pay for the change?
  - may have to find a creative way to implement it, or they may have to change the plan to accommodate it
- Informing Interested Parties
  - always inform the people who submitted the request of the team's decision
  - if requests are being ignored, they may take matters into their own hands and make changes without telling anyone
- Directing and Recording Changes
  - funnel all requests through the change control process
    - ensures that requests are fully analyzed and incorporated in a way that limits disruptions to the flow of the project
  - update records to reflect any implemented changes
  - communicate significant changes to the appropriate stakeholders

Reporting Performance
- Reporting Performance
  - team members need to monitor their performance closely and update the project manager with timely information
  - manager summarizes any important information and presents to stakeholders
    - document project performance
    - describe any inconsistencies or problems that the team may have encountered
- Completing Project Review Reports
  - status report
    - Scheduling information
      - Which activities did not run as planned?
      - Which tasks took shorter or longer than expected?
    - Cost updates
      - Which tasks went over or under budget?
    - Comparisons of effort
      - Did the effort expended to complete tasks match estimates?
    - Risk updates
      - Which risks occurred and what new risks should be considered?
  - place the information that is most critical to the audience at the top of the form
  - summarize work performance to a level of detail that makes sense for each stakeholder
  - compare expected performance to actual results and discuss the impact of any discrepancies
    - track project against the project baselines created in the Planning stage
- Presenting Information in Status Meetings
  - begin by focusing on good news that publicly acknowledges the team's hard work
  - use visual tools and graphics to show progress and to display accomplishments
  - recognize team success
  - enhance motivation by helping team members feel connected to the project and its goals
  - track any necessary action items on a spreadsheet and assign them to team members for follow-through
  - allow assigned team members to
    - discuss progress on the action items during team meetings
    - request help in completing assignments if needed
- Best Practices
  - for stakeholders with an advanced knowledge
    - include details such as cost variance/cost performance index numbers, schedule variance/schedule performance index data, critical ratios, estimate at completion, estimate to complete, and to-complete performance index information
  - include details about project risk
    - changes in the levels of risk on the project
    - trends that may suggest upcoming risks
    - a discussion of new risks that have been uncovered
    - the results of any implemented risk responses that have been put into effect
    - risks that have "passed" and are unlikely to occur
  - discuss project changes and work completed since the last status report

Performing Quality Control and Quality Assurance
- Performing Quality Control
  - measuring the extent to which results conform to the quality standards that were set
  - assess project results and make any necessary changes to improve performance
  - monitor quality issues for both products and processes throughout the life of the project
  - identify the reasons (root causes) behind the problems encountered so that solutions can be proposed that will eliminate the issues
- Quality Control Tools
  - Cause-and-effect diagrams
    - identify the correct problem to study and place it as a problem statement at the end of the diagram
    - fill out the "nodes" or "branches" on the diagram, arranging the causes of that problem according to their level of importance or detail
    - move from the problem statement back through each line of causality to develop a hierarchy of events that leads from the problem to the underlying root causes
  - Checksheets
    - a structured form or table that practitioners use to count how many times an event or problem happened, or to record when or where something happened
  - Flowcharts
    - define the process boundaries by picking the beginning and end points
    - then clearly define the relationships of all of the steps within those boundaries
    - might show what steps are allowing poor quality to enter a project
    - might show where quality monitoring and control activities can be placed to ensure that issues are resolved before work progresses
  - Control charts
    - upper and lower limits on the chart show measurements or values that the data cannot exceed
    - if its data points fall outside of these limits, the project is not meeting expectations and corrections must be made
  - Run charts
    - similar to control charts
    - focused on observing process performance over the long term
    - particularly helpful to show how many products have errors or how much variation a process is encountering over a period of time
    - help team see how corrections made in response to variations have resulted in improvements in quality
  - Histograms
    - shows how often things occur between categories
  - Pareto diagrams
    - type of histogram that sorts variables from most to least frequently occurring
    - Pareto's Law (the 80/20 principle)
      - 80% of the problems with a product or process can be attributed to 20% of the causes
  - Scatter diagrams
    - illustrate possible correlations between a dependent variable and an independent variable
    - just because the team has discovered a correlation, that doesn't mean that they've discovered the cause behind it
- Quality Assurance Tools
  - Affinity diagrams
    - group ideas into categories that can then be analyzed or evaluated
    - common themes or patterns emerge that can be used to break through bottlenecks or allow the team to clarify its thinking about issues or problems
    - uncover hidden relationships that may not have been noticed before
    - helps to filter and sift through ideas, tying concepts together and creating consensus about issues before additional work is begun
    - helps to ensure that all viewpoints are considered and prevents dominant personalities from taking over the process
    - useful for gathering and organizing ideas so they can be acted on or further developed
    - allow teams to analyze a lot of verbal or qualitative information so it can be used as an input to subsequent work
  - Process decision program charts
    - a tree diagram that is specifically designed to help teams mitigate risks and solve potential problems
    - steps
      - break a goal or objective down into major steps or activities
      - devise countermeasures or preventive actions
      - solve any potential problems that could happen during those activities
    - lowest tier of the PDPC illustrates the corrective and preventive actions that can be taken
  - Interrelationship digraphs
    - shows the cause-and-effect relationships among the many contributors to a problem
    - placed in a circle and arrows are drawn to show how each factor relates to every other factor
    - can identify root causes and develop effective strategies for addressing multiple factors simultaneously
    - help teams visualize relationships as a network of factors rather than as a linear cause-and-effect concept
    - a single factor is often affected by many drivers and may itself be the driver of many subsequent factors
    - helps teams understand where to focus their efforts to get the greatest benefits
    - helpful in instances where the symptoms of a problem are more visible than the underlying causes
  - Tree diagrams
    - uses successive steps to break things down into greater detail
    - can be used to uncover alternatives or to divide tasks into smaller increments for assignment
    - should include all of the possible outcomes or components that make up each level of the chart
  - Prioritization matrices
    - helps prioritize options when there are multiple criteria to satisfy at one time
    - each criterion may be more or less important to project success than other competing criteria
    - determine which ones are most important, then choose the options that are best for the project
    - criteria are assessed weights to ensure that decisions are based on information about the project rather than on emotions or feelings
  - Network diagrams
    - a simple graphic that shows the relationships among project activities
    - shows the predecessors as well as the successors for all of the activities in the project
    - helps the team:
      - Ensure that the project will continue to meet its expected schedule
      - Compare actual results to plans and see when corrections to the schedule are needed
      - Keep stakeholders informed about changes to the project's time line
  - Matrix diagrams
    - shows how strong the relationships between items or sets of items are
    - comparisons are compiled in a table for analysis and easy reference
    - help to expose gaps that should be addressed and focus the team's attention on high priority areas that should be tackled immediately

Utilizing Project Management Software
- to track, monitor, and control their project tasks and activities
- help make project progress readily apparent and quickly expose any problems or potential issues that may arise
- most are spreadsheet-based systems, but many have other graphic or charting capabilities
- Popular programs
  - Microsoft MS Project
  - Oracle Primavera Project Management Solutions
  - WorkZone
  - Smartsheet