Module 9: Project Closure and Closing Stage
9/13

Learning Objectives
1. Create a proposal for project execution, including implementation, schedule, and communication
2. Describe the controls for the project, including change management, risk management, and other issues related to project management
3. Create a plan for a project closeout, addressing tasks, a warranty period, and lessons learned
4. Create a project charter that can be implemented and executed within an organization

Closing the Project
- Why is Closing Necessary?
  - tell people that the project is over and that the project participants have completed their mission
  - ensures that all project activities are finished
    - that all milestones were met
    - that all project expenses are paid for
    - that all tasks related to the project's scope are complete
    - that any contracts used on the project are formally closed
      - all parts of the contract have been satisfied to the agreement of both parties
      - all necessary signatures have been obtained
      - all payments have been disbursed
  - ensures that stakeholders are satisfied that the project has met its objectives
    - members who were granted authority to declare that the project has met its objectives must agree that it has indeed met them
    - formal signatures from these parties may be necessary
  - ensures that the project's results are formally transitioned to subsequent stages and/or the project's end user
    - transfer deliverables to those responsible for them in operations or the next stage of the project life cycle
  - ensures that experiences and learning from the project are discussed and recorded for future use
    - elements such as evaluations, audits, and support documentation should also be collected and deposited into the organization's store of institutional knowledge
    - information about techniques that worked well and new knowledge gained is valuable to the success of future projects
    - if a project failed or was canceled, details about that project and any formal paperwork that accompanies its closure are especially
  - creates a formal space to celebrate and acknowledge those who did the project work

Closing Stage Tasks
- Reassigning personnel
  - individuals often face a certain amount of stress and anxiety toward the end of their projects
  - these feelings may be caused by the uncertainty about future work or from their pending separation and return to normal work activities
  - consider the psyche of team members because it can affect the ability to swiftly close the project
  - leaders should take an active role in helping team members integrate back into organizational roles
- Auditing final records
  - review and audit the project's final records or accounting documents to ensure that records reflect actual results and expenditures
  - leaders have a unique view of activities and results because they have been intimately involved in all aspects of the project
- Closing contracts
  - review existing contracts and to ensure that all obligations have been satisfied
- Creating support documents and product materials
  - provide the support material for the product created
  - may include user guides, owner's manuals, marketing material, or any other documents
- Communicating the completion of late-stage tasks and results to stakeholders
  - show stakeholders that several late-stage activities have been completed
  - communicate any changes or modifications that were incorporated late in the project
  - ensure that the plan to transition project results to their next phase is clearly documented and explained to all parties
- Completing a final report on the project
  - summarizes project activities and project results for the organization and key stakeholders
  - may include lessons learned on the project
    - leaders may choose to keep lessons learned information in a separate document for easier reference on future projects
- Project Closeout Checklist
  - describe all of the major steps in project loseout so team members can see which activities need to be quickly implemented to wrap up the project

The Project Retrospective Meeting
- final meeting to discuss lessons learned and to officially close the project
- allows the team to review the project as a whole and helps team members resolve any remaining issues before moving on to new assignments
- Suggestions
  - Be sure to invite everyone who contributed to the project to the final project review
    - invite contributors as early in the project as you can
    - solicit any ideas that they may have for improving future projects
    - consider using a three-part questionnaire to collect their impressions
      - rate the experience on a scale of 1–10
      - answer targeted questions to capture targeted feedback
      - include a comments section to let them provide open-ended/qualitative feedback
  - Record the results of the final project review and make them available to other teams
    - document contributions in writing
    - make lessons learned accessible across your organization
    - avoid using jargon or language that only participants on your project would understand
  - Start with a project overview to reacquaint everyone with the project's intended objectives
    - review the purpose and intended customer(s)
    - describe the initial design plans, the estimated budget, and the scheduled start and finish dates
  - Record the project details
    - final project description and any problems or defects you encountered
    - final budget and final release dates
    - development tools and processes you used and describe any innovations or process modifications you may have implemented
    - list the contributions of everyone who worked on the project to ensure that they receive proper credit and to document individuals future teams can turn to for expertise
  - Describe the project failures and successes
    - participants should review their project journals to remind themselves of their experiences on the project
    - record any suggestions that may have come up from project meetings
    - document any surprises you encountered during the project and how you responded
  - Take time to evaluate individual and team performance
    - record your impressions of teamwork, individual contributions, and newly acquired individual and team skills
  - Evaluate your project risk management activities
    - risks you took
    - how they turned out
    - suggestions about how you would change your approach on future projects
  - Develop conclusions and make suggestions
    - what you think you should start doing
    - what you should keep doing
    - what you should stop doing on future projects
  - Make sure all grievances and conflicts are addressed before moving on to new projects
  - Don't release team members to other projects until you have completed all project closure activities
    - make sure the team is available to complete any last minute items, clarify inconsistencies, and discuss lessons learned
  - Develop a plan of action for your own future projects
    - how you will incorporate the lessons you learned from this project into your upcoming projects
- ensure that final project reviews are not just meetings to rehash material that the team has already covered
- they should be constructive meetings that collect information but also provide plans for putting that information into action on future projects

Tips and Best Practices for Closing Projects
- Start thinking about closing the project very early in the project life cycle
  - picture what a successful project would look like and then work toward that vision
  - visualize what the project's end stage should be and think about all of the things that would make the Closing stage simpler and easier
- Remember that Closing is more than just handing off the product
  - consider the sustainability of the project results
  - consider how they can enhance the project's sustainability throughout its entire life cycle
  - picture what the project's final deliverable will look like a few years in the future
  - try to predict any issues or problems that may occur, then work to proactively reduce the probability and impact of those issues
- In retrospective meetings, remember what went right, too
  - this will ensure that future projects will benefit from its experience and run with fewer problems and difficulties
- Have an outside facilitator run the final lessons learned/project retrospective meeting
  - allows project leaders to join the discussion and contribute to conversations
- Make sure that lessons learned are more than just a "gut feeling"
  - including facts and data whenever possible will add details that will help future project participants understand and embrace suggestions as they plan their work