## Change Order Request Log
Final Project Change Order Log
Row ID	Change Request Description	Estimate of Level of Effort in Dollars	Change Request Approver	Approved Yes or No
1	Delay project start to mid-July	0	Peter McKenzie	No
2	Add additional IT team members	15000	Peter McKenzie	Yes
3	Extend interviews with subject matter experts to 21 days	22000	Tony DiBello	No
4	Give sales managers edit access to portal content	1800	Tony DiBello	Yes
5	Outsource case study content development	6500	Tony DiBello	No