## Communications Template
Item #	Required Time Frame (Daily, Weekly, Monthly, etc.)	Communication Title	Team Member Required to Receive Report	Required Method of Sharing Report (email, text, phone call, paper report, etc.)	Frequency	Team Member Assigned Task to produce communication
1	Weekly	General status updates	ALL stakeholders	Email	7 Days	Tony DiBello
2	Weekly	Content status updates	Non-IT stakeholders, product/sales employees, and subject matter experts	Email	7 Days	Richard Contin
3	Bi-Weekly	IT development status updates	ALL stakeholders	Paper report	14 Days	Steve Quan
4	Monthly	Checkpoint meeting	ALL team members and stakeholders	In person meeting	30 Days	Tony DiBello
5	Monthly	Completion and acceptance reports	ALL stakeholders	Posted on sharepoint	30 Days	Tony DiBello
6	Weekly	Team meetings	ALL team members	In person meeting	7 Days	Tony DiBello
7	By request	Ad-hoc status updates	Any requesters	Email	By request	Tony DiBello