## Stakeholder Concerns
Project Task Number	Description of Task	Planned Duration in Days	Planned Start Date	Planned Completion Date	Estimated Labor, Material, Etc. required to complete the project	Number of Units Required	Estimated Cost per Unit	Estimated Cost in Dollars
	Portal Development
1	User Interface Design Complete and Tested	2	06/01/19	06/03/19	Juan Felipe, System Engineer	10	6000	$60,000.00
2	Style Sheets for Portal	21	06/01/19	06/22/19	Monica Ianucci, Content Specialist	20	1500	$30,000.00
3	Theme Design for Website	56	06/03/19	07/29/19	Richard Contin, Director of Learning and Development	100	1800	$180,000.00
4	Portal Administration Complete and Accepted	2	06/03/19	06/05/19	Tony DiBello, Project Manager	5	680	$3,400.00
5	Administrative Page Groups	70	06/05/19	08/14/19	Juan Felipe, System Engineer	30	800	$24,000.00
6	Administrative Access Control Design	49	06/05/19	07/24/19	Susan Xiao, Lead Engineer	20	4500	$90,000.00
7	Content Management & Coding Complete and Tested	2	06/22/19	06/24/19	Monica Ianucci, Content Specialist	15	3000	$45,000.00
8	Content Display from Repository	28	06/24/19	07/22/19	Jonathan Brant, Content Specialist	62	1480	$91,760.00
9	Content Upload and Functionality	56	07/22/19	09/16/19	Richard Contin, Director of Learning and Development	4	500	$2,000.00
10	Configure/Code Indexing and Functionality	91	07/22/19	10/21/19	Steve Quan, Hightower IT Operations Specialist	250	2050	$512,500.00
	Infrastructure and Security
11	Architecture Approved for Implementation	1	07/29/19	07/30/19	Steve Quan, Hightower IT Operations Specialist	1	160	$160.00
12	Servers for Development, Staging, and Production	91	07/30/19	10/29/19	Shannon Valley, Hightower IT Systems and Security	25	450	$11,250.00
13	Configure Firewalls	28	07/30/19	08/27/19	Shannon Valley, Hightower IT Systems and Security	12	10000	$120,000.00
14	Integrate Infrastructure and Security Systems	56	07/30/19	09/24/19	Shannon Valley, Hightower IT Systems and Security	50	3200	$160,000.00
15	Log-in/Registration System Complete and Tested	3	08/27/19	08/30/19	Steve Quan, Hightower IT Operations Specialist	3	2000	$6,000.00
16	Create Log-in/User Profiles	28	08/30/19	09/27/19	Steve Quan, Hightower IT Operations Specialist	6	700	$4,200.00
	Content Creation and Editing
17	Product Content Modules Completed and Accepted	5	09/16/19	09/21/19	Richard Contin, Director of Learning and Development	10	250	$2,500.00
18	Interviews with Subject Matter Experts (SMEs) and Sales Representatives	14	09/21/19	10/05/19	Monica Ianucci, Content Specialist	40	800	$32,000.00
19	Product Sales Summaries	28	10/05/19	11/02/19	Richard Contin, Director of Learning and Development	120	550	$66,000.00
20	Sales Case Studies for Content Modules	49	10/05/19	11/23/19	Jonathan Brant, Content Specialist	35	100	$3,500.00
21	Edit/Film SME Videos	7	11/23/19	11/30/19	Monica Ianucci, Content Specialist	20	1000	$20,000.00
22	Upload Presentations, Demos, and Webinars for Content Modules	14	11/30/19	12/14/19	Jonathan Brant, Content Specialist	5	400	$2,000.00
	Documentation
23	Development and Document Coding Standards and Procedures	105	07/22/19	11/04/19	Steve Quan, Hightower IT Operations Specialist	200	5	$1,000.00
24	Develop Test Acceptance Plans and Procedures	105	09/10/19	12/24/19	Richard Contin, Director of Learning and Development	60	30	$1,800.00
25	HighLEARN Database Test and Acceptance	7	12/24/19	12/31/19	Steve Quan, Hightower IT Operations Specialist	75	100	$7,500.00
	HighLEARN Roll-out
Total Cost for Project	Product Content Modules Completed and Accepted							$1,476,570.00