## Risk Register
Risk Registser
Status	Risk ID Number	Identified Risk	Owner	Impact	Response -- Mitigation Plan
Closed	1	Website may not meet user requirements	Steve Quan	Medium	Checklist of requirements
In progress	2	Valley and Quan not available until July 15, 2019	Tony DiBello	High	Additional IT team members
Open	3	Associates may be unwilling to learn new tools	Richard Contin	Low	Presentation to associates
In progress	4	Language and communication barriers	Richard Contin	Low	Multiple tools and forms of content
Open	5	Portal may become outdated quickly with new acquisitons	Monica Ianucci	Medium	Monica will own updates upon project closure
Closed	6	Subject matter experts are busy during interview time period	Tony DiBello	Medium	Questionnaires will be adminstered outside of interview period

Template Legend
In progress			Team Member	Low
Delayed				Medium
Closed				High
Open