## Sheet1
Project Schedule with Tasks -- Duration/Resources-- Project Planning Part F
			2012		2013					2014
Project Tasks (ECO-Trans)	Duration in Days	Resource Assigned	Nov	Dec	Jan	Feb	Mar	Apr	May	June	July	Aug	Sep	Oct	Nov	Dec	Jan	Feb
Project initiation	100	Varga
System test	25	Operations
Confirm funding	10	Finance
Central control room	75	Engineers
Swap defective for new components	15	Varga
Equip first phase of locomotives	90	Engineers
Manually inspect new components	3	Varga
Reassemble terminal casings	7	Assembly Team
Reassign training specialists	10	Vonn/Beauchamp
Resolve resource calendar conflicts	1	Varga
Manage SRT team member conflict	5	Varga
Send product specialist for demo	2	Hermann
Equip entire fleet	30	Engineers
Complete end user training	6	Varga