## Stakeholder Concerns
Project Concern #	Description of Concern Identified	Impact on Project (High Medium, Low)	Date Identified	Due Date for Completion	Stakeholder that Identified Concern	Internal or External Stakeholder	Project Team Member Concern Assigned To:	Solution	Date Completed
1	Vivian Liu not trying to get bogged down	High	08/02/21	08/15/21	Janice Scott	Internal	Vivian Liu	Effective planning, no unnecessary steps	08/15/21
2	No lessons learned and WBS	Medium	08/10/21	09/01/21	Sam Massoni	External	Matt Stevens	Encourage team to reflect on past experiences and to make sure they understand their assigned responsibilities	08/30/21
3	Production team does not want to deal with the mess and disruption	Medium	08/14/21	10/09/21	Ken Simmons	Internal	Vivian Liu	Communicate with production so they can adjust their work locations during the execution of the lighting replacements	TBD