## Sheet1
Project Schedule with Milestones Project Planning Part E
| 2012 |  | 2013 | [11 empty] | 2014
Project Milestones (ECO-Trans) | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Project initiation | bar: 2012 Nov to 2013 Mar
System test | bar: 2013 Apr
Confirm funding | bar: 2013 May
Central control room | bar: 2013 June to 2013 Aug
Swap defective for new components | bar: 2013 Sep
Equip first phase of locomotives | bar: 2013 Sep to 2013 Dec
Manually inspect new components | bar: 2013 Oct
Reassemble terminal casings | bar: 2013 Oct
Reassign training specialists | bar: 2013 Oct
Resolve resource calendar conflicts | bar: 2013 Oct
Manage SRT team member conflict | bar: 2013 Nov
Send product specialist for demo | bar: 2013 Dec
Equip entire fleet | bar: 2014 Jan
Complete end user training | bar: 2014 Feb