## Sheet1
Project Schedule with Tasks -- Duration/Resources-- Project Planning Part F
|  |  | 2012 |  | 2013 | [11 empty] | 2014
Project Tasks (ECO-Trans) | Duration in Days | Resource Assigned | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Project initiation | 100 | Varga | bar: 2012 Nov to 2013 Mar
System test | 25 | Operations | bar: 2013 Apr
Confirm funding | 10 | Finance | bar: 2013 May
Central control room | 75 | Engineers | bar: 2013 June to 2013 Aug
Swap defective for new components | 15 | Varga | bar: 2013 Sep
Equip first phase of locomotives | 90 | Engineers | bar: 2013 Sep to 2013 Dec
Manually inspect new components | 3 | Varga | bar: 2013 Oct
Reassemble terminal casings | 7 | Assembly Team | bar: 2013 Oct
Reassign training specialists | 10 | Vonn/Beauchamp | bar: 2013 Oct
Resolve resource calendar conflicts | 1 | Varga | bar: 2013 Oct
Manage SRT team member conflict | 5 | Varga | bar: 2013 Nov
Send product specialist for demo | 2 | Hermann | bar: 2013 Dec
Equip entire fleet | 30 | Engineers | bar: 2014 Jan
Complete end user training | 6 | Varga | bar: 2014 Feb